CHANGE ORDER

────────────────────────────────────────────────────────────────────────

PROJECT INFORMATION

| Project: | Riverside Mixed-Use Development | Project #: | RMD-2024-001 |
| --- | --- | --- | --- |
| Change Order #: | CO-007 | Date: | March 5, 2025 |
| Owner: | Riverside Ventures LLC | Contractor: | IRONCLAD BUILDERS INC. |

OWNER

Riverside Ventures LLC

900 River Road, Suite 400, Sacramento, CA 95814

CONTRACTOR

Ironclad Builders Inc.

3300 Construction Avenue, Sacramento, CA 95826

DESCRIPTION OF CHANGE

Add fire suppression sprinkler system to parking structure levels 2-4. This change order is requested for the Riverside Mixed-Use Development project to comply with updated fire code requirements. Ironclad Builders Inc. shall provide all labor, materials, and equipment necessary for the installation.

COST AND SCHEDULE IMPACT

| Cost Impact: | Add $142,500.00 |
| --- | --- |
| Schedule Impact: | Add 12 working days |
| Original Contract Sum: | $18,500,000.00 |
| Previous Change Orders: | $0.00 |
| New Contract Sum: | $18,642,500.00 |

APPROVALS

Owner Approval:

___________________________________

Patricia Nakamura, VP of Development

Riverside Ventures LLC

Contractor Approval:

___________________________________

Frank Delgado, Project Director

Ironclad Builders Inc.

This change order CO-007 for project RMD-2024-001 has been reviewed and approved by Nakamura on behalf of Riverside Ventures and Delgado on behalf of Ironclad.